GuitarCoach

Revision 0.0.0 Developed by GuitarCoach Team

Sprint 4 Plan

Completion Date:  3/04/2026

Spring Information

Sprint Number: 4

Sprint Duration: February 25, 2026 – March 10, 2026

Sprint Goal: Finalize the core GuitarCoach MVP by completing the practice plan generation, weekly schedule view, and song-centered learning flow so that users have a fully working end-to-end experience.

Team Roles for this Sprint

Jackson: Full-Stack Developer, Product Owner

User Story 4, 14

MVP Cleanup

Erin: Full-Stack Developer

User Story 13, 4

MVP Cleanup

Joonhee: Full-Stack Developer, Scrum Master

MVP Cleanup

Kailyn: Front-End Developer

MVP Cleanup

User Stories and Development Tasks

User Story #13 – As a user, I want to be able to see a future practice schedule so that I have a plan of what to practice throughout the week. [5 story points]

- Create a weekly_schedule table in Supabase to store generated weekly plans [30 minutes]

- Develop backend logic for generating a user’s weekly practice schedule based on their progress and goals [3 hours]

- Create an API route to retrieve a user’s weekly schedule [1 hour]

- Design UI component for a weekly practice calendar or planner view for the week under a user’s dashboard [2 hours]

- Test schedule generation and ensure it updates dynamically when skill level changes [1 hour]

User Story #4 – As a user, I want my skills to be accurately described so that the practice plans match my ability. [5 story points – carryover refinement]

- Finalize Supabase skill tables and ensure questionnaire responses update correctly [1 hour]

- Test and verify that skill level values are correctly pulled and reflected in daily and weekly practice plans [2 hours]

- Refine logic to ensure the most accurate practice recommendations based on stored skill data [1 hour]

User Story #14 – As a user, I want to be able to center my practice around a specific song so that I can see what it will take to learn. [5 story points – stretch goal]

- Create logic that maps components of a song (e.g., bar chords, fingerpicking, tempo) to specific exercises [2 hours]

- Integrate Spotify search functionality with practice mapping logic [2 hours]

- Display required skill components for a selected song within the dashboard [1 hour]

Scrum Board

| User Story | To-Do | In-progress | Done |
| --- | --- | --- | --- |
| As a user, I want to be able to see what and how to practice so that I can improve. | Finalize “Today’s Practice” UI component Test recommendation accuracy across skill levels | Develop backend logic to generate daily practice plan Create /practice/today API route Connect dashboard to backend endpoint | Create practice_plan table in Supabase Successfully pull skill level data from Supabase |
| #13 As a user, I want to be able to see a future practice schedule so that I have a plan of what to practice throughout the week. | Create weekly_schedule table Develop weekly schedule generation logic Create /practice/week endpoint Design weekly planner UI |  |  |
| As a user, I want my skills to be accurately described so that the practice plans match my ability. | Refine skill-to-practice mapping logic |  | Finalize Supabase skill tables Ensure questionnaire updates skill values correctly |
| As a user, I want to be able to center my practice around a specific song so that I can see what it will take to learn. | Map song components to exercises Integrate Spotify search with practice mapping Display required skill breakdown |  |  |

`Scrum Times

Week 1 of Sprint 4:

2/25: Wednesday (online) @ 4:00 - 5:00 pm – TA Meeting

2/27: Friday (online) @ 3:00 - 3:40 pm

3/1: Sunday (online) @ 1:00 - 2:00 pm

Week 2 of Sprint 4:

3/2: Tuesday (in-person) @ 4:00 - 5:00 pm -  TA Meeting

3/3: Thursday (online) @ 4:00 - 4:40 pm

3/8: Sunday (online) @ 1:00 - 2:00 pm

Initial Burnup Chart